## Slide 1
 | Short term (0-12 months) |  | Medium term (12-24 months) |  | Long term (24-36 months) | 
Planning |  |  |  |  |  | 
Process |  |  |  |  |  | 
Systems |  |  |  |  |  | 
People |  |  |  |  |  | 
Project charter
Project plan
Project tracking
Project closure
Kick-off
Current state assessment
Future state process design
Future state detailed design
Legal/compliance/risk approvals
Stakeholder interviews
Procedure/process reviews
Initial tech meetings
Requirements
(System 1)
Requirements
(System 2)
Development (System 1)
Development (System 2)
Intakes
Testing
Testing
End-to-end Testing
Go-live
Change management
Training
Post go-live improvements
Performance measurement
Baseline measurement
New process implementation
We are here
Implementation Planning
tasko
consulting.com
Design workshops